## Tasks
Sr.No | Functionality | Task | Description | Type | Logged Date | Assigned to | Priority | Release Version | Status | Comments
1 | Payments and Pdc | When Payment transaction OR Paid Pdc is deleted then Reversal transaction is created but deleted transaction is not bind to this reversal transaction | Bind Deleted transaction to Reversal transaction | Defect | 2016-02-05 | Sunil | 2 | v2.0 | Open
2 | Entitlement Changes | Need to add entitlement for all pages | Need descriptive fucntional requirement |  | 2017-02-06 | Sunil | 3 | v2.0 | Closed
3 | Need to handle State state exception | In all application we need to handle stale state exception and show message 'Selected Record is modified by some other user. Please try again.' | Sudhir will do POC and implement in one of function. Then we will distribute pages. 16Feb - POC is done. Need to implement in all places This will be done along with Entitlement | Defect | 2017-02-09 |  | 2 | v2.0 | Open
4 | Values to be saved in DB without space | When UI text fields are populated in DTO, they should be trimmed to remove space before and after. |  | Requirement | 2017-02-09 |  | 1 | v2.0 | Open
5 | Demand Letter Tracking vs Unit | We need to capture data wheher demand letter for each stage is ready, given to customer or not. | New table will be added to store completed stage, demand letter ready, demand letter given. Add new column in above table to track last intimation sent. this will be datetime and will be updated when intimation is sent (From dashboard) When stage is marked as completed, on submit it will update all sold units with this completed stage entry in above new table . On stage is marked completed to inprogress then show warning (If demand letter is given to any of customer) and remove entry from above table |  | 2017-03-07 |  | 1 | v2.0 | Closed
6 | Add util method to validate session object | in page load method of every page, add method to validate type nav DTO of that page. this method will return same nav DTO of type is same of that page else returns null |  |  | 2017-11-08 | Sunil | 1 | v2.0 | Closed
7 | Handle hide/show of buttons effectively | On pages where buttons are hide n show dynamically and they are present inside li element then instead of button hide/show li element like manage property doc page | It ia low priority item |  |  |  | 3 | v2.0 | Closed
8 | Account n it's summary menu name change | Change name of account summary menu to Accounts. then each account row will hv account summary link |  | Requirement | 2017-11-13 |  | 1 | v2.0 | Open
9 | Letter generation code review | on Letter generation init method , pr unit sale details and property info is fetched which more than required... fetch info which ia required to reduce dB call |  | Defect | 2017-11-15 |  | 3 | v2.0 | Open
10 | Sold Unit Payments | Interest calculation on delayed payments | Need to design a functionality to autocalculate interest on delayed payments | Requirement | 2018-01-25 |  | 3 |  | Open
11 | Alerts and Gadgets | Dashboard gadgets -> There will be quick navigation between gadget and corresponding page - Upcoming Agreement/possession - Upcoming Pdc due - Due demand letters - Due receipt delivery | We can show these as dashboard gadgets OR in reports | Requirement | 2018-01-25 |  | 3 |  | Open
12 | Lead/Enquiry Activity | When open enquiry is reopened, confirmation msg is not shown. Also capture close reason for lead and enquiry Change 'Mark as Close' to 'Mark as Lost' | Show confirmation messgage "Enquiry will be reopened. Do you want to proceed?" | Defect | 2018-01-25 | Sunil | 1 | v2.0 | Closed
13 | Contact Number Format | Input contact number should be validated and saved in correct format. | We need to design system to capture contact in standard format. It may be mobile number/landline number etc. Discussion 25Jan: We will allow user to enter any number in contact/alt contact fields. System will not validate the format. Where as in order to match these numbers with exotel incoming/outgoing, below changes will be done 1. Update CallHistoryBO.fetchAgentForCall() method to match contact/altcontact ends with given number. 2. VW_CUSTOMER.sql should macth contact/alt contact ends with given number. This is required on ResolveCall page. 3. Add min 10 chars (If given) validation for contact and alt contact on all UI where it is accepted. | Requirement | 2018-01-25 | Sunil | 1 | v2.0 | Closed
14 | Call Autoresolve | For incoming call, we need to autoresolve the call. | For incoming call, system will find the Lead/Enquiry for incoming customer number. If it is single and OPEN then it will automatically add activity against it and show notification. In this case when CALL_INTIMATION is shown and user clicks on it then redirect to respective activity page. NOTE: No need to auto resolve the call against the sold unit. | Requirement | 2018-01-25 |  | 2 | v2.0 | Open
15 | Property Unit Upload | Direction and Facing dropdown in upload excel should be non-mandatory | When template is downloaded and Direction and Facing master codes not present then show empty dropdown for these fields. It should be uploaded with blank values. | Defect | 2018-01-25 | Sudhir | 1 | v2.0 | Closed
16 | Lead Upload | Need functionality to download and upload Leads through excel | Design functionality to bulk upload leads. | Requirement | 2018-01-25 | Sudhir | 1 | v2.0 | Open
17 | Property Listing portal integration | Need to have 99Acre, MagicBricks etc proeprty listing portal integration |  | Requirement | 2018-01-25 |  | 1 | v2.0 | Open
18 | Live chat inegration | Need to have live chat integration for leads |  | Requirement | 2018-01-25 |  | 1 | v2.0 | Open
19 | Property expenses | Need functionality for property expenses and related payments | Design functionality for property expenses and its payments | Requirement | 2018-01-25 |  | 2 |  | Open
20 | Marketting automation | Promotion management, Email templates, schedulers etc. |  | Requirement | 2018-01-25 |  | 3 |  | Open
21 | Reports | Need to have Presale and Post sale reports |  | Requirement | 2018-01-25 |  | 1 | v2.0 | Open
22 | Customer portal | Need to have customer portal. | Customer can log into the application for payment, receipts, log request | Requirement | 2018-01-25 |  | 3 |  | Open
23 | Payment gateway Inegration | Need to have payment gateway integration so that customer can do payment |  | Requirement | 2018-01-25 |  | 3 |  | Open
24 | Change password | Add change password functionality. | Add menu in top right dropdown for change password | Requirement | 2018-01-25 | Sunil | 1 |  | Closed
25 | Duplicate lead/Enquiry | Add functionality to validate duplicate lead/enquiry | Lead/Enquiry is added with duplicate contact number - User adds Lead/Enquiry - on submit check whether same contact exist in another OPEN lead/Enquiry of same Property - If Yes, then show warning message to user OR do now allow to add it - Lead generated from Social/real estate portal - If another lead/enquiry found with OPEN status, same contact and property then add activity indicating enquiry done by user - In case Enquiry is re-opened then also check whether other enquiry is open with same contact and property | Defect | 2018-01-25 | Sunil | 1 | v2.0 | Closed
26 | Broker/Agent Management | Assign Units to Broker/Manage Broker Sold Units/Manage Broker Payments |  | Requirement | 2018-01-25 |  | 3 |  | Open
27 | Generate Agreement | generate agreement in PDF format |  | Requirement | 2018-01-25 |  | 3 |  | Open
28 | Twitter Integration | Leads should be created through twitter |  | Requirement | 2018-01-25 |  | 2 |  | Open
29 | Configure agent and edit agent info | Agent contact number should be unique | On Edit profile page add validation to check contact number of agent is unique in all agents | Defect | 2018-01-25 | Sunil | 1 |  | Closed
30 | Make a Call on Resolve Call page | In case of missed call/unresolved calls, agent can call back customer from this page. | Add 'Make a Call' button on resolve call page. | Requirement | 2018-01-30 | Sunil | 1 | v2.0 | Closed
31 | Property Name | Property name should be unique in DB | Validate property name unique in adding new property | Defect | 2018-01-30 |  | 1 | v2.0 | Closed
32 | Javascript Script manager error on deployed app on Web | Getting below javascript error on website Uncaught TypeError: n is not a constructor at f.create (ScriptResource.axd?d=GByFs6wshV4X_zdCroetdsATvjBA-9XKG4Zw5_kvy-DY3dMK-SXK0dXqXC6DNvh0TtiKRyURJ1vbC4C0Ho60V0aXfN4PXdQ7fMYaFEUqJcFJAcj5l2thnRqKDb8SLiQ_0&t=51e37521:2) at Array.<anonymous> (PropertyDetails:1213) at ScriptResource.axd?d=GByFs6wshV4X_zdCroetdsATvjBA-9XKG4Zw5_kvy-DY3dMK-SXK0dXqXC6DNvh0TtiKRyURJ1vbC4C0Ho60V0aXfN4PXdQ7fMYaFEUqJcFJAcj5l2thnRqKDb8SLiQ_0&t=51e37521:2 | Need to check solution given in below URL https://stackoverflow.com/questions/39494490/asp-net-c-sharp-ajaxcontroltoolkit-timer-malfunction-with-updatepanel | Defect | 2018-02-01 | Sudhir | 1 | v2.0 | Open
33 | Search Filter change | In all filters, we need to provide functionality to search given string in data | Use Case Insensitive like at all places. | Defect | 2018-02-02 | Sudhir | 1 | v2.0 | Open
34 | Notifications | Add close and clear all buttons in notification panel |  | Requirement | 2018-02-02 | Sunil | 1 | v2.0 | Open
35 | Default page of function menu | In Default dashboard pages of function menu - Notification messages are not getting formatted | Copy common pre-render and other code. Also check for other pages like error pages | Defect | 2018-02-02 | Sunil | 1 | v2.0 | Closed
36 | Error messages | Validation errors shown in page header should be moved to noty msg | All validation/exception error (Except modals) should be moved to noty messages and show error icon at right of page header in case more errors | Requirement | 2018-02-02 | Sunil | 1 | v2.0 | Closed
37 | Password validation | Password should have restrictions to make it stronger | Add password restrictions - Atleast 1 character/number/special char - Min legth 8 | Requirement | 2018-02-04 | Sunil | 1 | v2.0 | Open
38 | User login once | User should be logged in once.. if logged in from another machine then log out previous login |  | Requirement | 2018-02-04 | Sunil | 1 | v2.0 | Open
39 | Page unneccesary scrolls up | When error has occurred in modal then page should not be scrolled up |  | Requirement | 2018-02-04 | Sunil | 1 | v2.0 | Closed
40 | Manage property Docs | Property details should be same as User access page |  | Defect | 2018-02-04 | Sunil | 1 | v2.0 | Closed
41 | Property Unit template | When property unit upload template is downloaded, it is not opening. |  | Defect | 2018-02-04 | Sudhir | 1 | v2.0 | Open
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
Defect
Requirement
Technical-task
Analysis

## Go live tasks
Sr.No | Functionality | Task | Description | Logged Date | Assigned to | Priority | Release Version | Status | Comments